## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US-01 | System Authentication | As a Application User, I want to register and log in securely, so that I can access my role-specific dashboard. | Must Have | 1 | 1. User must select a role (TA or MO). 2. Data MUST be stored in local .json/.txt files (No DB). 3. Show error message on invalid credentials. | 5 | NO DATABASE allowed | 15/03/2026 | 15/03/2026
US-02 | Post TA Job | As a Module Organiser, I want to post new wanted, so that candidates can view and apply. | Must Have | 1 | 1. Only MO can access the "Post Job" page. 2. Must include Module Code, Description, and Capacity. 3. Job data successfully serialized to local text file. | 3 |  | 16/03/2026 | 16/03/2026
US-03 | Browse Job Hall | As a Teaching Assistant, I want to browse all available TA jobs in a hall, so that I can find suitable work | Must Have | 1 | 1. TA's default homepage is the Job Hall. 2. List dynamically loaded from local file. 3. Displays key info (Module, MO name, Status). | 3 |  | 16/03/2026 | 17/03/2026
US-04 | Creat TA's Profile | As a Teaching Assistant, I want to create my profile and upload a CV, so that MOs can evaluate my qualifications. | Must Have | 2 | 1. TA can input skills and grades. 2. System supports PDF/DOCX CV uploads. 3. File paths are saved within the user's JSON data. | 5 | File upload mechanism required. | 17/03/2026 | 19/03/2026
US-05 | Apply for Job | As a Teaching Assistant, I want to apply for an interesting job with one click and upload my profile, So that I can compete for the position. | Must Have | 2 | 1. Clicking "Apply" generates an application record linking TA and Job. 2. TA cannot apply for the same job twice. 3. Application data saved to file. | 3 |  | 18/03/2026 | 19/03/2026
US-06 | Manage Applications | As a Module Organiser, I want to review applicants and accept or reject them, So that I can finalize TA selection. | Must Have | 2 | 1. MO sees a list of applicants and their CVs. 2. MO can update status to "Accepted" or "Rejected". 3. Thread-safe file writing to prevent data corruption. | 5 | Requires file locking for concurrent writes. | 18/03/2026 | 19/03/2026